## StudentWork
Management Information Systems Project Management Homework
Leave Column C blank if it would have the same value as column B
Leave Columns F-H blank
| Estimated | Estimated | Calculated
| Person | Elapsed | Elapsed |  | Start | Completion
Task Description | Hours | Time (Days) | Hours | Assigned to | Date | Date
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## MillerExample
Management Information Systems Project Management Homework
Leave Column C blank if it would have the same value as column B
Leave Columns F-H blank
| Estimated | Estimated | Calculated
| Person | Elapsed | Elapsed |  | Start | Completion
Task Description | Hours | Time (Days) | Hours | Assigned to | Date | Date
Rename old Assignment | 0.1 |  | 0.1
Hide old Assignment in all modules | 0.2 |  | 0.2
Create new Assignment | 1.5 |  | 1.5
Add new Assignment to Modules | 0.3 |  | 0.3
Create Assignment questions | 1 |  | 1
Write instrucions document in Dreamweaver | 2 |  | 2
Create Excel Template | 1 |  | 1
Research Basecamp | 1.5 |  | 1.5
Add Basecamp video links to instruction document | 0.5 |  | 0.5
Research monday.com | 1.5 |  | 1.5
Add monday.com links to instruction document | 0.5 |  | 0.5
Upload instrucions and Excel Workbook to millerjw.com | 0.2 |  | 0.2
Update all instructions to reference uploaded documents | 0.3 |  | 0.3
Use Camtasia to record setting up Monday.com account | 1 |  | 1
Use Camtasia to record setting up Workspaces and Projects | 1 |  | 1
Use Camtasia to combine and Edit all video clips | 0.5 | 0.12 | 0.96
Upload the video to milerjw.com | 0.1 | 0.06 | 0.48
Create a page in Canvas that references all videos | 0.5 |  | 0